## Main
Scrum Project
Product | Timesheet Application
Active versions | 1.5
Team
Scrum Master | Nguyen Thanh Dat
Developers | Dang Viet Trung
Nguyen Dinh Luan
Vo Ngoc Khoa
Product Owner | Nguyen Thanh Dat
Projects | [5 empty] | Sprint Plan
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Story Points (Committed) | Story Points (Delivered) | Remarks
1 | Update task in sprint 1 | 2021-06-09 | 30/09/2021 | Done |  | 1 | 2021-06-09 | 30/09/2021 | Done | 160 | 254
2 | Update task in sprint 2 | 2021-01-10 | 26/10/2021 | Done |  | 2 | 2021-01-10 | 26/10/2021 | Done | 468 | 378
3 | Update task in sprint 3 | 27/10/2021 | 20/11/2021 | Done |  | 3 | 27/10/2021 | 20/11/2021 | Done | 371 | 401
4 | Update task in sprint 4 | 21/11/2021 | 2021-12-12 | Done |  | 4 | 21/11/2021 | 2021-12-12 | Done | 208 | 229

## Backlog
Backlog
Id | Epics | As a.. | I want to .. | so that .. | Acceptance Criteria | Priority | Project Id | Sprint Id | Story Points (Est.) | Effort (Actual) | Owner | Status | Remarks
PB01 | Login | Product Owner, Manager, Employee | Access to the app | I can use the app | Step 1 : Enter into email and password + Email is required + Password is required + Capcha is required Step 2 : Click into Login button | 3 | 1 | 1 | 24 | 59 | Luan,Dat,Khoa | Done
PB02 | Login using QR Code | Product Owner, Manager, Employee | Access to the app faster | I can use the app | Step 1 : Open mobile app which has loged in + QR Code is required Step 2 : Scan the QR Code on the website | 3 | 1 | 1 | 12 | 22 | Dat | Done
PB03 | Register | Product Owner | Create an account | I can use the app | Step 1 : Enter into all the field - Email is based on email format minimum 7 characters , contains alpha characters and digits and is required - Password minimum 10 characters , contains alpha characters , special characters and digits , minimum 1 uppercase , minimum 1 lowercase , minimum 1 digits , minimum 1 specical character and is required - Name of Organization contains alpha characters and numbers , minimum 3 characters - Country contains alpha characters and numbers , minimum 3 characters - City contains alpha characters and numbers , minimum 3 characters - Area contains alpha characters and numbers , minimum 3 characters - Street name contains alpha characters and numbers , minimum 3 characters - Street code contains alpha characters and numbers , minimum 1 characters - Capcha is required Step 2 : Click into Register button Step 3 : Wait a little and the notification will show | 3 | 1 | 1 | 24 | 39 | Luan, Dat,Khoa | Done
PB04 | Project Management | Product Owner | Create a project | I can manage the project | Step 1 : Click into My Organization Step 2 : Click into Project Management - Project Name is minimum 3 digits , contains alpha characters and numbersand is required - Description contains alpha characters and numbers - Start date is a date type - End date is a date type - Budget is a number and it's greater than 0 Step 3 ; Click into Add Project button | 3 | 1 | 1 | 80 | 80 | All members | Done
PB05 | Member Management | Product Owner | Create members for organization | I can manage members | Step 1 : Click into Member Management Step 2 : Enter all fields - Email is based on email format minimum 7 characters , contains alpha characters and numbers and is required - Password minimum 8 characters , contains alpha characters , special characters and digits , minimum 1 uppercase , minimum 1 lowercase , minimum 1 digits , minimum 1 specical character and is required - First Name minimum 1 characters , contains alpha characters and is required - Last Name minimum 2 characters , contains alpha characters and is required - Department is required - Position is required Step 3 : Click into Add Member button | 2 | 2 | 2 | 45 | 19 | Dat,Khoa | Done
PB06 | Postion Management | Product Owner | Add a position | I can manage memebers by the position | Step 1 : Access into Position Management Step 2 : Enter all fields - Position name contains alpla characters and digits , minimum 3 characters and maximum 20 characters and is required - Position description is not required Step 3 : Click into Add Position button | 2 | 2 | 2 | 15 | 15 | Dat,Khoa | Done
PB07 | Team Assignment | Manager | Add members into the team | I can manage members in the team | Step 1 : Access into Department Management Step 2 : Choose a member to add into the team Step 3 : Click into Add Member button | 2 | 2 | 2 | 25 | 25 | Dat,Khoa | Done
PB08 | Mailbox | Product Owner, Manager, Employee | Send mail | I can notify to members | Step 1 : Click into Mailbox Step 2 : Click into Compose mail Step 3 : Enter receiver address , content Step 4 : Click into Send button | 2 | 3 | 3 | 60 | 53 | Trung,Dat,Khoa | Done
PB09 | Project Management | Product Owner | Add teams | I can manage a project by the teams | Step 1 : Access into Team Management Step 2 : Enter all fields - Team name contains alpla characters and digits , minimum 3 characters and maximum 20 characters and is required - Team description is not required - Team budget contains number and it's greater than 0 - Manager of Team is required - Project Name is required Step 3 : Click into Create button | 2 | 2 | 2 | 15 | 15 | Dat,Khoa | Done
PB10 | Expense & Timesheet Report | Employee | Show my timesheets and expenses | I can know detail information about my timesheets and expenses | Step 1 : Access into Expense Report Step 2 : Enter all fields - Expense Type is required - Expense Cost is number and it's greater than 0 - Expense Image is not required - Expense Description is not requried - Expense Date is required Step 3 : Click into Add Expense button | 2 | 2 | 2 | 40 | 26 | Luan,Dat,Khoa | Done
PB11 | Expense & Timesheet Management | Manager | Show all timesheets | I can manage all timesheets in the team | Step 1 : Access into Expense Management Step 2 : Enter all fields - Expense Status is required Step 3 : Click into Edit Expense button | 2 | 2 | 2 | 45 | 25 | Dat,Khoa | Done
PB12 | Department Management | Product Owner | Add departments | I can manage members by the departments | Step 1 : Access into Department Management Step 2 : Enter all fields - Department Name contain numbers or alpha characters and minimum 3 characters - Department Description is not required Step 3 : Click into Add Department button | 2 | 2 | 2 | 15 | 15 | Dat,Khoa | Done
PB13 | Taskboard | Product Owner, Manager | Create tasks | I can assign tasks for the employees | Step 1 : Acess into Taskboard Step 2 : Click into Add a list button Step 3 : Enter all fields for a list - List Name contain numbers or alpha characters and minimum 3 characters Step 4 : Click into Add button Step 5 : Click into Add a card button Step 6 : Enter title - Title contain numbers or alpha characters and minimum 3 characters Step 6 : Enter all fields for a task - Task Name contain numbers or alpha characters and minimum 3 characters - Task Description is not required - Task Members is required - Task Priority is required | 2 | 3 | 3 | 112 | 117 | All members | Done
PB14 | Budget Project | Product Owner | Show budget statistical | I can manage budget in the project |  | 2 | 2 | 2 | 36 | 27 | Luan,Dat,Khoa | Done
PB15 | Progress Project | Product Owner | Show progress statistical | I can manage progress in the project |  | 2 | 2 | 2 | 24 | 22 | Dat,Khoa | Done
PB16 | Expense & Timesheet Summary | Employee | Statistic my timesheets and expenses | I can track my timesheets and expenses |  | 2 | 2 | 2 | 32 | 27 | Dat,Khoa | Done
PB17 | Calendar | Manager, Employee | Show my calendar | I can manage my schedule |  | 2 | 3 | 3 | 32 | 45 | All members | Done
PB18 | Expense and Timsheet Statistic | Manager | Statistic my team | I can manage my team |  | 2 | 2 | 2 | 48 | 51 | Trung,Dat,Khoa | Done
PB19 | Project List | Manager, Employee | Access a project | I can use the dashboard |  | 2 | 2 | 2 | 24 | 26 | Luan,Trung,Khoa | Done
PB20 | Take attendance with QR code | Employee | Scan my QR code | I can take attendant | Step 1 : Login into app Step 2 : Choose a project Step 3 : Put QR code in front of camera to take attendant | 2 | 3 | 3 | 36 | 28 | Dat,Khoa | Done
PB21 | Notes Management | Product Owner, Manager, Employee | See Timesheet statistic | I can know timesheet statistic | Step 1 : Click into Timesheets Statistics Step 2 : App will show statistics | 2 | 3 | 3 | 48 | 60 | Trung,Dat,Khoa | Done
PB22 | Chat | Product Owner, Manager, Employee | Send messages | I can contact with members | Step 1 : Click into Chat Step 2 : Choose a member Step 2 : Send a message - Message contains alpha characters and digits , minimum 3 characters and is required | 2 | 2 | 2 | 80 | 45 | All members | Done
PB23 | File Manager | Product Owner, Manager, Employee | Save file | I can manage files | Step 1 : Click into File Manager Step 2 : Upload a file or create a folder - File name contains alpha characters and digits , minimum 3 characters and is required - Folder name contains alpha characters and digits , minimum 3 characters and is required | 2 | 4 | 4 | 56 | 58 | Dat | Done
PB24 | My Team | Manager, Employee | Show my team | I can know my team in the project |  | 2 | 3 | 3 | 24 | 25 | Trung,Dat,Khoa | Done
PB25 | Profile | Manager, Employee | Edit profile | I can change the profile | Step 1 : Click into My Profile Step 2 : Update my profile - Email is based on email format minimum 7 characters , contains alpha characters and numbers and is required - Password minimum 10 characters contains alpha characters and numbers and is required - Fullname minimum 3 characters , contains alpha characters and numbers and is required - Gender contains Male/Female is required - Phone number contains 11 digits and is required - Country contains alpha characters and numbers , minimum 3 characters - City contains alpha characters and numbers , minimum 3 characters - Area contains alpha characters and numbers , minimum 3 characters - Street name contains alpha characters and numbers , minimum 3 characters - Street code contains alpha characters and numbers , minimum 1 characters - Department is required - Position is required | 1 | 4 | 4 | 36 | 44 | Trung,Dat,Khoa | Done
PB26 | Download Page | Product Owner, Manager, Employee | Download mobile app | I can use on mobile device | Step 1 : Click into Download Step 2 : Download app with platforms | 1 | 4 | 4 | 16 | 24 | Luan | Done
PB27 | About Page | Product Owner, Manager, Employee | See information about app | I can understand more about app | Step 1 : Click into About Step 2 : App will show About page | 1 | 4 | 4 | 16 | 18 | Luan | Done
PB28 | Home Page | Product Owner, Manager, Employee | See introduction about app | I can know app | Step 1 : Click into Home Step 2 : App will show Home page | 1 | 1 | 1 | 8 | 25 | Trung | Done
PB29 | Testcase Sprint 1 | Tester | Know errors in the app | I can fix errors |  | 2 | 1 | 1 | 12 | 27 | Khoa | Done
PB30 | Testcase Sprint 2 | Tester | Know errors in the app | I can fix errors |  | 2 | 2 | 2 | 12 | 16 | Khoa | Done
PB31 | Testcase Sprint 3 | Tester | Know errors in the app | I can fix errors |  | 2 | 3 | 3 | 12 | 16 | Khoa | Done
PB32 | Testcase Sprint 4 | Tester | Know errors in the app | I can fix errors |  | 2 | 4 | 4 | 12 | 7 | Khoa | Done
PB33 | Task List | Manager, Employee | Show my tasks | I can complete my tasks |  | 2 | 4 | 4 | 36 | 31 | Luan,Dat,Khoa | Done

## Sprint Task 1
Overtime
End
To do
Sprint Task 1 | [26 empty] | Before the time
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Actual | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25
1 | PB01 | Design UI Mock Up | Luan | Done | 2 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | PB01 | Develop HTML/CSS/Typescript | Luan,Dat | Done | 15 | 26 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 11 | 7 | 3 | 1 | 1 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | PB01 | Develop Backend | Dat,Khoa | Done | 7 | 28 | 7 | 7 | 7 | 7 | 7 | 7 | 7 |  | 7 | 3 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | PB03 | Design UI Mock Up | Luan | Done | 2 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | PB03 | Develop HTML/CSS/Typescript | Luan | Done | 15 | 21 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 11 | 11 | 11 | 7 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | PB03 | Develop Backend | Khoa | Done | 7 | 13 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | PB04 | Design UI Mock Up | Trung,Luan | Done | 5 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
1 | PB04 | Develop HTML/CSS/Typescript | Trung,Luan | Done | 45 | 29 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 40 | 40 | 40 | 32 | 24 | 16 | 16
1 | PB04 | Develop Backend | Dat,Khoa | Done | 30 | 24 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 24 | 18 | 18 | 18 | 12 | 8 | 6 | 6
1 | PB28 | Design UI Mock Up | Trung | Done | 2 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | PB28 | Develop HTML/CSS/Typescript | Trung | Done | 6 | 21 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 2 | 2 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0
1 | PB29 | Testcase Sprint 1 | Trung,Luan | Done | 24 | 27 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 16 | 8 | 3 | 0
|  |  |  | Total | 160 | 206
|  |  |  | Estimate |  |  | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 153 | 160 | 146 | 138 | 131 | 126 | 126 | 124 | 111 | 112 | 95 | 84 | 84 | 84 | 62 | 42 | 24 | 24
|  |  |  | Actual |  |  | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 153 | 160 | 150 | 142 | 135 | 130 | 130 | 126 | 114 | 115 | 106 | 89 | 89 | 84 | 62 | 42 | 27 | 24
No | Member Name | Hours available per Sprint
1 | Dang Viet Trung | 44
2 | Nguyen Dinh Luan | 37
3 | Nguyen Thanh Dat | 65
4 | Vo Ngoc Khoa | 60

## Sprint Task 2
Overtime
End
To do
Sprint Task 2 | [28 empty] | Before the time
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Actual | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27
2 | PB04 | Design UI Mock Up | Trung,Luan | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB04 | Develop HTML/CSS/Typescript | Trung,Luan | Done | 16 | 16 | 11 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB04 | Develop Backend | Dat,Khoa | Done | 6 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB07 | Design UI Mock Up | Trung | Done | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB07 | Develop HTML/CSS/Typescript | Trung | Done | 15 | 15 | 15 | 15 | 15 | 9 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB07 | Develop Backend | Dat,Khoa | Done | 7 | 7 | 7 | 7 | 7 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB11 | Design UI Mock Up | Dat | Done | 3 | 3 | 5 | 5 | 5 | 5 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB11 | Develop HTML/CSS/Typescript | Dat | Done | 20 | 11 | 20 | 20 | 20 | 20 | 20 | 16 | 12 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB11 | Develop Backend | Khoa | Done | 14 | 11 | 14 | 14 | 14 | 14 | 14 | 10 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB10 | Design UI Mock Up | Luan | Done | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB10 | Develop HTML/CSS/Typescript | Dat,Luan | Done | 29 | 11 | 29 | 29 | 29 | 29 | 29 | 29 | 25 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 4 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB10 | Develop Backend | Khoa | Done | 15 | 11 | 15 | 15 | 15 | 15 | 15 | 15 | 11 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB12 | Design UI Mock Up | Trung | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB12 | Develop HTML/CSS/Typescript | Trung | Done | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB12 | Develop Backend | Dat | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB06 | Design UI Mock Up | Dat | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB06 | Develop HTML/CSS/Typescript | Khoa | Done | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB06 | Develop Backend | Khoa | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB05 | Design UI Mock Up | Trung | Done | 5 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB05 | Develop HTML/CSS/Typescript | Trung | Done | 25 | 8 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 21 | 21 | 21 | 21 | 21 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB05 | Develop Backend | Dat,Khoa | Done | 15 | 8 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 11 | 11 | 11 | 11 | 11 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB09 | Design UI Mock Up | Trung | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB09 | Develop HTML/CSS/Typescript | Trung | Done | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB09 | Develop Backend | Dat,Khoa | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB15 | Design UI Mock Up | Dat | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB15 | Develop HTML/CSS/Typescript | Dat | Done | 15 | 13 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 7 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 0 | 0
2 | PB15 | Develop Backend | Khoa | Done | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
2 | PB16 | Design UI Mock Up | Dat | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0
2 | PB16 | Develop HTML/CSS/Typescript | Dat | Done | 20 | 15 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 14 | 8 | 3 | 0 | 0
2 | PB16 | Develop Backend | Khoa | Done | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 6 | 3 | 0 | 0 | 0
2 | PB18 | Design UI Mock Up | Trung | Done | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB18 | Develop HTML/CSS/Typescript | Trung,Dat | Done | 29 | 29 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 12 | 3 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB18 | Develop Backend | Khoa | Done | 15 | 18 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0
2 | PB14 | Design UI Mock Up | Luan | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB14 | Develop HTML/CSS/Typescript | Luan,Dat | Done | 15 | 17 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB14 | Develop Backend | Khoa | Done | 7 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB22 | Design UI Mock Up | Trung,Luan | Done | 5 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0 | 0 | 0 | 0 | 0
2 |  | Develop HTML/CSS/Typescript | Trung,Luan | Done | 50 | 24 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 42 | 34 | 8 | 0 | 0 | 0
2 | PB22 | Develop Backend | Dat,Khoa | Done | 25 | 19 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 20 | 12 | 6 | 0 | 0 | 0
2 | PB19 | Design UI Mock Up | Luan,Trung | Done | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB19 | Develop HTML/CSS/Typescript | Luan,Trung | Done | 15 | 16 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB19 | Develop Backend | Dat | Done | 7 | 8 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | PB30 | Testcase Sprint 2 | Khoa | Done | 12 | 16 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 4 | 0
|  |  |  | Total | 468 | 378
|  |  |  | Estimate |  |  | 433 | 414 | 414 | 401 | 393 | 379 | 358 | 356 | 332 | 332 | 315 | 305 | 291 | 275 | 257 | 247 | 247 | 235 | 231 | 217 | 195 | 176 | 147 | 119 | 109 | 99 | 99
|  |  |  | Actual |  |  | 433 | 416 | 414 | 401 | 393 | 379 | 358 | 340 | 320 | 320 | 303 | 293 | 279 | 266 | 248 | 222 | 212 | 200 | 196 | 182 | 146 | 119 | 87 | 41 | 10 | 4 | 0
No. | Member Name | Hours available per Sprint
1 | Dang Viet Trung | 85
2 | Nguyen Dinh Luan | 76
3 | Nguyen Thanh Dat | 109
4 | Vo Ngoc Khoa | 108

## Sprint Task 3
Overtime
End
To do
Sprint Task 3 | [26 empty] | Before the time
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25
3 | PB20 | Design UI Mock Up | Luan | Done | 3 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PB20 | Develop HTML/CSS/Typescript | Luan | Done | 20 | 8 | 16 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PB20 | Develop Backend | Khoa,Dat | Done | 13 | 16 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PB24 | Design UI Mock Up | Trung | Done | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PB24 | Develop HTML/CSS/Typescript | Trung | Done | 13 | 7 | 13 | 13 | 13 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PB24 | Develop Backend | Dat,Khoa | Done | 9 | 16 | 9 | 9 | 9 | 1 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PB13 | Design UI Mock Up | Luan,Trung,Dat | Done | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PB13 | Develop HTML/CSS/Typescript | Luan,Trung,Dat | Done | 64 | 79 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 64 | 56 | 46 | 33 | 21 | 7 | 3 | 6 | 6 | 0 | 0 | 0 | 0
3 | PB13 | Develop Backend | Khoa | Done | 40 | 30 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 36 | 32 | 28 | 24 | 20 | 18 | 14 | 4 | 0 | 0 | 0 | 0
3 | PB02 | Design UI Mock Up | Dat | Done | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PB02 | Develop HTML/CSS/Typescript | Dat | Done | 7 | 10 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 3 | 3 | 3 | 3 | 3 | 1 | 2 | 0 | 0 | 0 | 0 | 0
3 | PB02 | Develop Backend | Dat | Done | 3 | 10 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PB08 | Design UI Mock Up | Trung | Done | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 2 | 1 | 0
3 | PB08 | Develop HTML/CSS/Typescript | Trung | In Progress | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 33 | 33 | 26 | 24 | 22 | 20
3 | PB08 | Develop Backend | Dat,Khoa | In Progress | 20 | 28 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 14 | 8 | 2 | 8
3 | PB21 | Design UI Mock Up | Trung | In Progress | 5 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 1 | 1
3 | PB21 | Develop HTML/CSS/Typescript | Trung | In Progress | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 2 | 2 | 2
3 | PB21 | Develop Backend | Dat,Khoa | In Progress | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
3 | PB17 | Design UI Mock Up | Luan,Trung | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PB17 | Develop HTML/CSS/Typescript | Luan,Trung | Done | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 14 | 14 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PB17 | Develop Backend | Khoa,Dat | Done | 11 | 24 | 11 | 11 | 11 | 11 | 11 | 3 | 3 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PB33 | Design UI Mock Up | Luan | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PB33 | Develop HTML/CSS/Typescript | Luan | Done | 23 | 12 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 19 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 4 | 0 | 0 | 0 | 0
3 | PB33 | Develop Backend | Dat,Khoa | Done | 10 | 16 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PB31 | Testcase Sprint 3 | Khoa | Done | 12 | 16 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 4 | 0
|  |  |  | Total | 371 | 401
|  |  |  | Estimate |  |  | 357 | 351 | 347 | 334 | 331 | 312 | 312 | 301 | 301 | 301 | 301 | 280 | 274 | 252 | 236 | 217 | 199 | 181 | 169 | 161 | 161 | 136 | 95 | 80 | 74
|  |  |  | Actual |  |  | 357 | 343 | 335 | 322 | 322 | 296 | 296 | 290 | 293 | 285 | 285 | 264 | 264 | 244 | 220 | 201 | 183 | 165 | 157 | 153 | 130 | 99 | 58 | 47 | 46
No. | Member Name | Hours available per Sprint
1 | Dang Viet Trung | 90
2 | Nguyen Dinh Luan | 81
3 | Nguyen Thanh Dat | 116
4 | Vo Ngoc Khoa | 114

## Sprint Task 4
Overtime
End
To do
Sprint Task 4 | [23 empty] | Before the time
<- effort / day ->
Sprint Id | Backlog Id | Description | Owner | Status | Story Points (Est.) | Completed | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22
4 | PB21 | Develop HTML/CSS/Typescript | Trung | Done | 2 | 7 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PB21 | Develop Backend | Dat,Khoa | Done | 15 | 22 | 15 | 15 | 15 | 15 | 15 | 9 | 9 | 9 | 4 | 1 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PB08 | Develop HTML/CSS/Typescript | Trung | Done | 20 | 11 | 18 | 12 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PB23 | Design UI Mock Up | Luan | Done | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PB23 | Develop HTML/CSS/Typescript | Dat,Luan | Done | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 26 | 26 | 26 | 22 | 17 | 11 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PB23 | Develop Backend | Dat | Done | 22 | 24 | 22 | 22 | 22 | 22 | 22 | 18 | 18 | 18 | 14 | 10 | 6 | 2 | 2 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
4 | PB25 | Design UI Mock Up | Trung | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
4 | PB25 | Develop HTML/CSS/Typescript | Dat,Trung | Done | 22 | 24 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 16 | 10 | 4 | 2 | 0 | 0
4 | PB25 | Develop Backend | Khoa | Done | 12 | 18 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 1 | 5 | 0 | 0
4 | PB26 | Design UI Mock Up | Luan | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
4 | PB26 | Develop HTML/CSS/Typescript | Luan,Trung | Done | 14 | 22 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 9 | 6 | 8 | 0
4 | PB27 | Design UI Mock Up | Luan | Done | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
4 | PB27 | Develop HTML/CSS/Typescript | Luan,Dat | Done | 14 | 16 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 6 | 6 | 0
4 | PB32 | Testcase Sprint 4 | Khoa | Done | 12 | 17 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 6 | 1 | 5 | 0
|  |  |  | Total | 173 | 201
|  |  |  | Estimate |  |  | 171 | 165 | 165 | 160 | 160 | 144 | 144 | 144 | 129 | 128 | 104 | 94 | 87 | 87 | 87 | 87 | 75 | 65 | 42 | 22 | 7 | 0
|  |  |  | Actual |  |  | 171 | 165 | 158 | 153 | 153 | 137 | 137 | 137 | 122 | 109 | 108 | 87 | 86 | 84 | 84 | 84 | 68 | 58 | 36 | 22 | 19 | 0
No. | Member Name | Hours available per Sprint
1 | Dang Viet Trung | 48
2 | Nguyen Dinh Luan | 41
3 | Nguyen Thanh Dat | 57
4 | Vo Ngoc Khoa | 55

## Impediment
Impediments |  | Raised By | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Remarks
Id | Description
PB04 | Meet errors and bugs while develop the features | Project Management | Sprint 1 | PB04 | Dat,Khoa | Accomplished | Optimize and spend more time edit source code
PB13 | Complex and have many features | Taskboard | Sprint 3 | PB13 | Trung,Luan,Dat,Khoa | Accomplished | Have meeting and need more time
PB08 | Real-time features are obstacles and complex | Mailbox | Sprint 3 | PB08 | Trung,Dat,Khoa | Accomplished | Spend more time reading source code to manage data flow from React
PB21 | Users can't add notes | Notes Management | Sprint 3 | PB21 | Trung,Dat,Khoa | Accomplished | Assign for the tester

## Retrospective
Retrospective Log |  |  |  | Start Doing | Stop Doing | Remarks
Sprint # | Date | Owner | Continue Doing
Sprint 1 | 2021-06-09 | Khoa,Dat |  | Design Database |  | In Progress
Sprint 1 | 2021-08-09 | Khoa,Dat | Design Database |  |  | In Progress
Sprint 1 | 2021-09-09 | Khoa,Dat | Design Database |  |  | In Progress
Sprint 1 | 2021-10-09 | Khoa,Dat | Design Database |  |  | In Progress
Sprint 1 | 2021-12-09 | Khoa,Dat | Design Database |  |  | In Progress
Sprint 1 | 14/9/2021 | Khoa,Dat |  |  | Design Database | Accomplished
Sprint 1 | 15/9/2021 | Luan,Dat,Khoa |  | Develop Login |  | In Progress
Sprint 1 |  | Luan,Khoa |  | Develop Register |  | In Progress
Product Owner | 2021-10-09 | Luan,Dat,Khoa | Develop Login |  |  | In Progress
Sprint 1 |  | Luan,Khoa | Develop Register |  |  | In Progress
Sprint 1 |  | Luan,Dat,Khoa | Develop Login |  |  | In Progress
Sprint 1 | 17/9/2021 | Luan,Khoa | Develop Register |  |  | In Progress
Sprint 1 | 18/9/2021 | Luan,Dat,Khoa | Develop Login |  |  | In Progress
Sprint 1 | 18/9/2021 | Luan,Khoa | Develop Register |  |  | In Progress
Sprint 1 | 19/9/2021 | Luan,Dat,Khoa | Develop Login |  |  | In Progress
Sprint 1 | 19/9/2021 | Luan,Khoa | Develop Register |  |  | In Progress
Sprint 1 | 20/9/2021 | Luan,Dat,Khoa | Develop Login |  |  | In Progress
Sprint 1 | 20/9/2021 | Luan,Khoa | Develop Register |  |  | In Progress
Sprint 1 | 20/9/2021 | Trung |  | Develop Home page |  | In Progress
Sprint 1 | 21/9/2021 | Trung | Develop Home page |  |  | Accomplished
Sprint 1 | 21/9/2021 | Luan,Khoa | Develop Register |  |  | In Progress
Sprint 1 | 22/9/2021 | Luan,Dat,Khoa |  |  | Develop Login | Accomplished
Sprint 1 | 22/9/2021 | Luan,Khoa | Develop Register |  |  | Accomplished
Sprint 1 | 23/9/2021 | Luan,Khoa |  |  | Develop Register | Accomplished
Sprint 1 | 23/9/2021 | Trung |  |  | Develop Home page | Accomplished
Sprint 1 | 23/9/2021 | All Member |  | Project Management |  | In Progress
Sprint 1 | 23/9/2021 | Trung | Home Page | Home Page |  | In Progress
Sprint 1 | 24/9/2021 | All Member | Project Management |  |  | In Progress
Sprint 1 | 24/9/2021 | Trung | Home Page |  |  | In Progress
Sprint 1 | 25/9/2021 | Trung |  |  | Home Page | Accomplished
Sprint 1 | 27/9/2021 | Trung,Luan |  | Testcase Sprint 1 |  | In Progress
Sprint 1 | 27/9/2021 | All Member | Project Management |  |  | In Progress
Sprint 1 | 28/9/2021 | Trung,Luan | Testcase Sprint 1 |  |  | In Progress
Sprint 1 | 28/9/2021 | All Member | Project Management |  |  | In Progress
Sprint 1 | 29/9/2021 | Trung,Luan | Testcase Sprint 1 |  |  | Accomplished
Sprint 1 | 29/9/2021 | All Member | Project Management |  |  | In Progress
Sprint 1 | 30/9/2021 | All Member | Project Management |  |  | In Progress
Sprint 2 |  | All Member | Project Management |  |  | In Progress
Sprint 2 | 2021-01-10 | Luan,Dat,Trung |  | Project List |  | In Progress
Sprint 2 | 2021-02-10 | All Member | Project Management |  |  | In Progress
Sprint 2 | 2021-02-10 | Luan,Dat,Trung |  |  | Project List | Accomplished
Sprint 2 | 2021-04-10 | Trung,Dat,Khoa |  | Team Assignment |  | In Progress
Sprint 2 | 2021-05-10 | Trung,Dat,Khoa | Team Assignment |  |  | Accomplished
Sprint 2 | 2021-06-10 | Khoa,Dat |  | Expense & Timesheet Management |  | In Progress
Sprint 2 | 2021-07-10 | Khoa,Dat |  | Expense & Timesheet Management |  | Accomplished
Sprint 2 | 2021-07-10 | Luan,Dat,Khoa |  | Expense & Timesheet Report |  | In Progress
Sprint 2 | 2021-08-10 | Luan,Dat,Khoa |  | Expense & Timesheet Report |  | In Progress
Sprint 2 | 2021-09-10 | Trung,Dat |  | Department Management |  | In Progress
Sprint 2 | 2021-09-10 | Khoa,Dat |  | Position Management |  | In Progress
Sprint 2 | 2021-11-10 | Trung,Dat,Khoa |  | Member Management |  | In Progress
Sprint 2 | 2021-11-10 | Trung,Dat,Khoa |  | Team Management |  | In Progress
Sprint 2 | 2021-12-10 | Khoa,Dat |  | Progress Project |  | In Progress
Sprint 2 | 13/10/2021 | Luan,Dat,Khoa |  | Budget Project |  | In Progress
Sprint 2 | 14/10/2021 | Khoa,Dat | Progress Project |  |  | In Progress
Sprint 2 | 14/10/2021 | Luan,Dat,Khoa |  |  | Budget Project | Accomplished
Sprint 2 | 15/10/2021 | Trung,Dat |  |  | Department Management | Accomplished
Sprint 2 | 15/10/2021 | Trung,Dat,Khoa |  |  | Team Management | Accomplished
Sprint 2 | 16/10/2021 | Trung,Dat,Khoa |  |  | Member Management | Accomplished
Sprint 2 | 18/10/2021 | Khoa,Dat |  |  | Position Management | Accomplished
Sprint 2 | 19/10/2021 | All Member |  |  | Project Management | Accomplished
Sprint 2 | 20/10/2021 | Trung,Dat,Khoa |  | Expense & Timesheet Statistic |  | In Progress
Sprint 2 | 21/10/2021 | Trung,Dat,Khoa | Expense & Timesheet Statistic |  |  | In Progress
Sprint 2 | 21/10/2021 | Luan,Dat,Khoa |  |  | Expense & Timesheet Report | Accomplished
Sprint 2 | 22/10/2021 | Trung,Dat,Khoa | Expense & Timesheet Statistic |  |  | In Progress
Sprint 2 | 22/10/2021 | All Member |  | Chat |  | In Progress
Sprint 2 | 23/10/2021 | Khoa,Dat |  | Expense & Timesheet Summary |  | In Progress
Sprint 2 | 23/10/2021 | All Member | Chat |  |  | In Progress
Sprint 2 | 24/10/2021 | Khoa,Dat | Expense & Timesheet Summary |  |  | In Progress
Sprint 2 | 24/10/2021 | Khoa |  | Testcase Sprint 2 |  | In Progress
Sprint 2 | 24/10/2021 | Trung,Dat,Khoa | Expense & Timesheet Statistic |  |  | In Progress
Sprint 2 | 24/10/2021 | All Member |  |  | Chat | Accomplished
Sprint 2 | 25/10/2021 | Khoa,Dat |  |  | Expense & Timesheet Summary | Accomplished
Sprint 2 | 25/10/2021 | Khoa | Testcase Sprint 2 |  |  | In Progress
Sprint 2 | 25/10/2021 | Trung,Dat,Khoa |  |  | Expense & Timesheet Statistic | Accomplished
Sprint 2 | 25/10/2021 | Khoa,Dat |  |  | Progress Project | Accomplished
Sprint 2 | 26/10/2021 | Khoa |  |  | Testcase Sprint 2 | Accomplished
Sprint 3 | 27/10/2021 | Luan,Dat,Khoa |  | Take attendant with QR code |  | In Progress
Sprint 3 | 28/10/2021 | Luan,Dat,Khoa |  |  | Take attendant with QR code | Accomplished
Sprint 3 | 30/10/2021 | Trung,Dat,Khoa |  | My Team |  | In Progress
Sprint 3 | 31/10/2021 | Trung,Dat,Khoa |  |  | My Team | Accomplished
Sprint 3 | 2021-01-11 | All Member |  | Calendar |  | In Progress
Sprint 3 | 2021-03-11 | All Member | Calendar |  |  | In Progress
Sprint 3 | 2021-04-11 | All Member | Calendar |  |  | In Progress
Sprint 3 | 2021-07-11 | All Member | Calendar |  |  | In Progress
Sprint 3 | 2021-08-11 | All Member |  |  | Calendar | Accomplished
Sprint 3 | 2021-09-11 | Dat |  | Login using QR Code |  | In Progress
Sprint 3 | 2021-09-11 | All Member |  | Taskboard |  | In Progress
Sprint 3 | 2021-10-11 | All Member | Taskboard |  |  | In Progress
Sprint 3 | 2021-11-11 | All Member | Taskboard |  |  | In Progress
Sprint 3 | 2021-11-11 | All Member |  |  |  | In Progress
Sprint 3 | 2021-12-11 | All Member | Taskboard |  |  | In Progress
Sprint 3 | 13/11/2021 | All Member | Taskboard |  |  | In Progress
Sprint 3 | 14/11/2021 | All Member | Taskboard |  |  | In Progress
Sprint 3 | 15/11/2021 | All Member | Taskboard |  |  | In Progress
Sprint 3 | 15/11/2021 | Trung,Dat,Khoa |  | Mailbox |  | In Progress
Sprint 3 | 16/11/2021 | All Member | Taskboard |  |  | In Progress
Sprint 3 | 17/11/2021 | Khoa |  | Testcase Sprint 3 |  | In Progress
Sprint 3 | 17/11/2021 | All Member | Taskboard |  |  | In Progress
Sprint 3 | 17/11/2021 | Trung,Dat,Khoa | Mailbox |  |  | In Progress
Sprint 3 | 18/11/2021 | Khoa | Testcase Sprint 3 |  |  | In Progress
Sprint 3 | 18/11/2021 | All Member |  |  | Taskboard | Accomplished
Sprint 3 | 18/11/2021 | Trung,Dat,Khoa | Mailbox |  |  | In Progress
Sprint 3 | 18/11/2021 | Trung,Dat,Khoa |  | Note Management |  | In Progress
Sprint 3 | 19/11/2021 | Khoa |  |  | Testcase Sprint 3 | Accomplished
Sprint 3 | 19/11/2021 | Trung,Dat,Khoa | Mailbox |  |  | In Progress
Sprint 3 | 19/11/2021 | Trung,Dat,Khoa | Note Management |  |  | In Progress
Sprint 3 | 20/11/2021 | Trung,Dat,Khoa | Mailbox |  |  | In Progress
Sprint 3 | 20/11/2021 | Trung,Dat,Khoa | Note Management |  |  | In Progress
Sprint 4 | 21/11/2021 | Trung,Dat,Khoa | Mailbox |  |  | In Progress
Sprint 4 | 22/11/2021 | Trung,Dat,Khoa | Mailbox |  |  | In Progress
Sprint 4 | 23/11/2021 | Trung,Dat,Khoa |  |  | Mailbox | Accomplished
Sprint 4 | 24/11/2021 | Dat | Login using QR Code |  |  | In Progress
Sprint 4 | 25/11/2021 | Dat |  |  | Login using QR Code | Accomplished
Sprint 4 | 26/11/2021 | Luan,Dat |  | File Manager |  | In Progress
Sprint 4 | 26/11/2021 | Trung,Dat,Khoa | Note Management |  |  | In Progress
Sprint 4 | 27/11/2021 | Trung,Dat,Khoa | Note Management |  |  | In Progress
Sprint 4 | 27/11/2021 | Luan,Dat | File Manager |  |  | In Progress
Sprint 4 | 28/11/2021 | Trung,Dat,Khoa | Note Management |  |  | In Progress
Sprint 4 | 28/11/2021 | Luan,Dat | File Manager |  |  | In Progress
Sprint 4 | 29/11/2021 | Trung,Dat,Khoa | Note Management |  |  | In Progress
Sprint 4 | 30/11/2021 | Trung,Dat,Khoa | Note Management |  |  | In Progress
Sprint 4 | 30/11/2021 | Luan,Dat | File Manager |  |  | In Progress
Sprint 4 | 2021-01-12 | Trung,Dat,Khoa |  |  | Note Management | Accomplished
Sprint 4 | 2021-01-12 | Luan,Dat | File Manager |  |  | In Progress
Sprint 4 | 2021-02-12 | Luan,Dat | File Manager |  |  | In Progress
Sprint 4 | 2021-03-12 | Luan,Dat | File Manager |  |  | In Progress
Sprint 4 | 2021-04-12 | Luan,Dat | File Manager |  |  | In Progress
Sprint 4 | 2021-05-12 | Luan,Dat | File Manager |  |  | In Progress
Sprint 4 | 2021-06-12 | Luan,Dat |  |  | File Manager | Accomplished
Sprint 4 | 2021-07-12 | Trung,Dat,Khoa |  | Profile |  | In Progress
Sprint 4 | 2021-08-12 | Trung,Dat,Khoa | Profile |  |  | In Progress
Sprint 4 | 2021-09-12 | Trung,Dat,Khoa | Profile |  |  | In Progress
Sprint 4 | 2021-09-12 | Luan,Trung |  | Download Page |  | In Progress
Sprint 4 | 2021-09-12 | Khoa |  | Testcase Sprint 4 |  | In Progress
Sprint 4 | 2021-10-12 | Trung,Dat,Khoa |  |  | Profile | Accomplished
Sprint 4 | 2021-10-12 | Luan,Trung | Download Page |  |  | In Progress
Sprint 4 | 2021-10-12 | Khoa | Testcase Sprint 4 |  |  | In Progress
Sprint 4 | 2021-10-12 | Luan,Dat |  | About Page |  | In Progress
Sprint 4 | 2021-11-12 | Luan,Trung | Download Page |  |  | In Progress
Sprint 4 | 2021-11-12 | Khoa | Testcase Sprint 4 |  |  | In Progress
Sprint 4 | 2021-11-12 | Luan,Dat | About Page |  |  | In Progress
Sprint 4 | 2021-12-12 | Luan,Trung |  |  | Download Page | Accomplished
Sprint 4 | 2021-12-12 | Khoa |  |  | Testcase Sprint 4 | Accomplished
Sprint 4 | 2021-12-12 | Luan,Dat |  |  | About Page | Accomplished

## References
References
External |  | Internal
Description | Link | Description | Link
Burn Down Chart Analysis | https://viblo.asia/p/scrum-burndown-chart-cach-phan-tich-tien-do-dieu-chinh-sprint-thong-qua-burndown-chart-oOVlYMarl8W
How to use backlogs | https://www.agilealliance.org/glossary/backlog/