## Estimated
SPRINT 1 PLANNING
Team Availability
| Name | Available Hours | Estimation Total
| Tien | 76 | 288 | [10 empty] | On Time
| Phuoc | 88 | [11 empty] | Lately
| Huy | 52 | [11 empty] | Early
| Dat | 72 | [11 empty] | Unfinished
Sprint | Component | Task name | Responsible Member | Total | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18
1 | Initial Sprint 1 | Sprint Planning Meeting | All member | 16 | 0
|  | Create Sprint Backlog for Sprint 1 | Tien | 4 | 4 | 0
|  | Create Test Plan document for Sprint 1 | Tien | 4 | 4 | 4 | 0
| Design | Design UI for the Home | Dat | 4 | 4 | 4 | 0
|  | Design UI for the Login | Dat | 4 | 4 | 4 | 0
|  | Design UI for the Logout | Dat | 4 | 4 | 4 | 0
|  | Design UI for the Register | Dat | 4 | 4 | 4 | 0
|  | Design UI for the User Information | Huy | 4 | 4 | 4 | 0
|  | Design UI for the Manage Mentor | Huy | 4 | 4 | 4 | 0
|  | Design UI for the Manage Notification | Huy | 4 | 4 | 4 | 0
|  | Design UI for User Information | Huy | 4 | 4 | 4 | 0
|  | Design Test Case | Phuoc | 8 | 8 | 4 | 0
| Code | [Front-end] Home [User] | Huy | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Login [User] | Dat | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Logout [User] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Register [User] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] User Information [User] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Update Information [User] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] List Account[User[Admin]] | Huy | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Update Account[User[Admin]] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Create Account[User[Admin]] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end]get List Students[User[Moderator]] | Huy | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Create Students[User[Moderator]] | Huy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Update Students[User[Moderator]] | Huy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Introduce Capstone[User] | Huy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end]get List Mentor[User[Moderator]] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end]Update Mentor[User[Moderator]] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] get list Notification[User] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] update Notification[User[Moderator]] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Sign in [User] | Tien | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] Register to execute capstone | Tien | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] get All Account[User] | Phuoc | 4 | 4 | 4 | 4 | 0
|  | [Back-end] insert Account[User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] delete Account[User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] update Account[User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] get All Student[User] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] delete Student[User] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] approve for Student[User] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] update Student[User] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] get All Mentor [User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] insert Mentor [User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] delete Mentor[User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] update Mentor [User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] export file Mentor [User] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] get All Notification[User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Create Notification[User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] delete Notification[User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] update Notification[User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Testing | Test All Funtion | Tien, Phuoc | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 0
| Fix bug | Fix bug for Sprint 1 | Tien, Phuoc | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
| Re-testing | Re-Testing for Sprint 1 | Tien, Phuoc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 24 | 8 | 8 | 8 | 0
| Close | Spring Review meeting | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
|  | Retrospective | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
|  |  |  | 288 | 272 | 264 | 224 | 216 | 204 | 184 | 168 | 156 | 140 | 124 | 108 | 100 | 100 | 68 | 64 | 48 | 16 | 0

## Actual
SPRINT 1 PLANNING
Team Availability
| Name | Available Hours | Estimation Total
| Tien | 68 | 276 | [11 empty] | On Time
| Phuoc | 84 | [12 empty] | Lately
| Huy | 52 | [12 empty] | Early
| Dat | 72 | [12 empty] | Unfinished
Sprint | Component | Task name | Responsible Member | Total | Actual | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18
1 | Initial Sprint 1 | Sprint Planning Meeting | All member | 16 | 16 | 0
|  | Create Sprint Backlog for Sprint 1 | Tien | 4 | 4 | 4 | 0
|  | Create Test Plan document for Sprint 1 | Tien | 4 | 4 | 4 | 4 | 0
| Design | Design UI for the Home | Dat | 4 | 4 | 4 | 4 | 0
|  | Design UI for the Login | Dat | 4 | 4 | 4 | 4 | 0
|  | Design UI for the Logout | Dat | 4 | 4 | 4 | 4 | 0
|  | Design UI for the Register | Dat | 4 | 4 | 4 | 4 | 0
|  | Design UI for the User Information | Huy | 4 | 4 | 4 | 4 | 0
|  | Design UI for the Manage Mentor | Huy | 4 | 4 | 4 | 4 | 0
|  | Design UI for the Manage Notification | Huy | 4 | 4 | 4 | 4 | 0
|  | Design UI for User Information | Huy | 4 | 4 | 4 | 4 | 0
|  | Design Test Case | Phuoc | 8 | 8 | 8 | 4 | 0
| Code | [Front-end] Home [User] | Huy | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Login [User] | Dat | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Logout [User] | Dat | 4 | 0 | 4 | 4 | 4 | 4 | 0
-4
|  | [Front-end] Register [User] | Dat | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 0
-4
|  | [Front-end] User Information [User] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Update Information [User] | Dat | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
-4
|  | [Front-end] List Account[User[Admin]] | Huy | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Update Account[User[Admin]] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Create Account[User[Admin]] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end]get List Students[User[Moderator]] | Huy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Create Students[User[Moderator]] | Huy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Update Students[User[Moderator]] | Huy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Introduce Capstone[User] | Huy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end]get List Mentor[User[Moderator]] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end]Update Mentor[User[Moderator]] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] get list Notification[User] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] update Notification[User[Moderator]] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Sign in [User] | Tien | 8 | 4 | 8 | 8 | 8 | 4 | 0
-4
|  | [Back-end] Register to execute capstone | Tien | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] get All Account[User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] insert Account[User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] delete Account[User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] update Account[User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] get All Student[User] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] delete Student[User] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] approve for Student[User] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] update Student[User] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] get All Mentor [User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] insert Mentor [User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] delete Mentor[User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] update Mentor [User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] export file Mentor [User] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] get All Notification[User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Create Notification[User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] delete Notification[User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] update Notification[User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Testing | Test All Funtion | Tien, Phuoc | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 0
| Fix bug | Fix bug for Sprint 1 | Tien, Phuoc | 16 | 8 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
-8
| Re-testing | Re-Testing for Sprint 1 | Tien, Phuoc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 24 | 8 | 8 | 8 | 0
| Close | Spring Review meeting | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
|  | Retrospective | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
|  |  |  | 288 | 264 | 272 | 264 | 224 | 208 | 184 | 172 | 156 | 136 | 124 | 112 | 100 | 92 | 96 | 64 | 64 | 48 | 8 | 0

## Burn Down Chart
Estimated | Actual | Date
272 | 272 | 2022-03-01
264 | 264 | 2022-03-02
224 | 224 | 2022-03-03
216 | 208 | 2022-03-04
204 | 184 | 2022-03-05
184 | 176 | 2022-03-06
172 | 168 | 2022-03-07
164 | 152 | 2022-03-08
152 | 140 | 2022-03-09
136 | 128 | 2022-03-10
120 | 116 | 2022-03-11
104 | 100 | 2022-03-12
100 | 100 | 2022-03-13
68 | 64 | 2022-03-14
64 | 64 | 2022-03-15
48 | 48 | 2022-03-16
16 | 8 | 2022-03-17
0 | 0 | 2022-03-18