## Estimate
SPRINT 2 PLANNING
Team Availability
| Name | Available Hours | Estimation Total
| Tien | 92 | 384 | [10 empty] | On Time
| Phuoc | 96 | [11 empty] | Lately
| Huy | 100 | [11 empty] | Early
| Dat | 96 | [11 empty] | Unfinished
Sprint | Component | Task name | Responsible Member | Total | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13
2 | Initial Sprint 2 | Sprint Planning Meeting | All member | 16 | 0
|  | Create Sprint Backlog for Sprint 2 | Tien | 4 | 4 | 0
|  | Create Test Plan document for Sprint 2 | Tien | 4 | 4 | 4 | 0
| Design | Design UI for Manage Group | Huy | 12 | 12 | 8 | 4 | 0
|  | Design UI for Manage Topic | Dat | 12 | 12 | 8 | 4 | 0
|  | Design UI for Manage File Template | Dat | 4 | 4 | 4 | 4 | 4 | 0
|  | Design Test Case | Phuoc | 8 | 8 | 4 | 0
| Code | [Front-end] List Group [User] | Huy | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0
|  | [Front-end] detail Group [User] | Huy | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0
|  | [Front-end] Create Group [Moderator] | Huy | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0
|  | [Front-end] update Group [Moderator] | Huy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Front-end] assign mentor for Group [Moderator] | Huy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Front-end] Delete Group [Moderator] | Huy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Submit Topic[User[Student]] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Update Topic[User[Student]] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Topic List[User] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Detail Topic[User] | Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Front-end]Approve Topic[User[Moderator]] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end]Submit Topic Template[User[Moderator]] | Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Front-end] Topic template List[User] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end]Upload file Topic Template[User] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Group List [User] | Tien | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] detail Group [User] | Tien | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] Group List of mentor [Mentor] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Create Group [Moderator] | Tien | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] update Group [Moderator] | Tien | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] assign mentor for Group [Moderator] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Delete Group [Moderator] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] export file Group List [Moderator] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Submit Topic of Student[Student] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Submit Topic of mentor[Mentor] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Upload file Topic template[Mentor] | Phuoc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] approve for Student[Moderator] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Topic Student List [User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Topic template List [User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] update topic [Student] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] update topic [Mentor] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] delete topic[Student] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] delete topic[Mentor] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] export file Topic Student List[Moderator] | Phuoc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] Upload file document template[Moderator] | Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
| Testing | Test All Funtion | All member | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 16 | 0
| Fix bug | Fix bug for Sprint 2 | All member | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 32 | 16 | 0
| Re-testing | Re-Testing for Sprint 2 | Tien, Phuoc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 24 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
| Close | Spring Review meeting | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
|  | Retrospective | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
|  |  |  | 384 | 368 | 352 | 336 | 328 | 324 | 308 | 292 | 276 | 260 | 244 | 224 | 208 | 208 | 172 | 156 | 140 | 128 | 108 | 88 | 72 | 56 | 40 | 36 | 32 | 16 | 0

## Acutal
SPRINT 2 PLANNING
Team Availability
| Name | Available Hours | Estimation Total
| Tien | 92 | 376 | [11 empty] | On Time
| Phuoc | 96 | [12 empty] | Lately
| Huy | 100 | [12 empty] | Early
| Dat | 88 | [12 empty] | Unfinished
Sprint | Component | Task name | Responsible Member | Total | Actual | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13
2 | Initial Sprint 2 | Sprint Planning Meeting | All member | 16 | 16 | 0
|  | Create Sprint Backlog for Sprint 2 | Tien | 4 | 4 | 4 | 0
|  | Create Test Plan document for Sprint 2 | Tien | 4 | 4 | 4 | 4 | 0
| Design | Design UI for Manage Group | Huy | 12 | 12 | 12 | 8 | 4 | 0
|  | Design UI for Manage Topic | Dat | 12 | 12 | 12 | 8 | 4 | 0
|  | Design UI for Manage File Template | Dat | 4 | 0 | 4 | 4 | 4 | 4 | 0
-4
|  | Design Test Case | Phuoc | 8 | 8 | 8 | 4 | 0
| Code | [Front-end] List Group [User] | Huy | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0
|  | [Front-end] detail Group [User] | Huy | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0
|  | [Front-end] Create Group [Moderator] | Huy | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0
|  | [Front-end] update Group [Moderator] | Huy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Front-end] assign mentor for Group [Moderator] | Huy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Front-end] Delete Group [Moderator] | Huy | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Submit Topic[User[Student]] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Update Topic[User[Student]] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Topic List[User] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end] Detail Topic[User] | Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Front-end]Approve Topic[User[Moderator]] | Dat | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
-4
|  | [Front-end]Submit Topic Template[User[Moderator]] | Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Front-end] Topic template List[User] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Front-end]Upload file Topic Template[User] | Dat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Group List of mentor [Mentor] | Tien | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] detail Group [User] | Tien | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] Group List of mentor [Mentor] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Create Group [Moderator] | Tien | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] update Group [Moderator] | Tien | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] assign mentor for Group [Moderator] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Delete Group [Moderator] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] export file Group List [Moderator] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Submit Topic of Student[Student] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Submit Topic of mentor[Mentor] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Upload file Topic template[Mentor] | Phuoc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] approve for Student[Moderator] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Topic Student List [User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Topic template List [User] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] update topic [Student] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] update topic [Mentor] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] delete topic[Student] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] delete topic[Mentor] | Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] export file Topic Student List[Moderator] | Phuoc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] Upload file document template[Moderator] | Dat | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
| Testing | Test All Funtion | All member | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 16 | 0
| Fix bug | Fix bug for Sprint 2 | All member | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 32 | 16 | 0
| Re-testing | Re-Testing for Sprint 2 | Tien, Phuoc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 24 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
| Close | Spring Review meeting | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
|  | Retrospective | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
|  |  |  | 384 | 376 | 368 | 352 | 336 | 328 | 320 | 308 | 292 | 276 | 260 | 244 | 220 | 208 | 208 | 172 | 156 | 140 | 128 | 108 | 88 | 72 | 56 | 40 | 36 | 32 | 16 | 0

## Burn Down Chart
Estimated | Actual | Date
368 | 368 | 2022-03-19
352 | 352 | 2022-03-20
336 | 336 | 2022-03-21
328 | 328 | 2022-03-22
324 | 320 | 2022-03-23
308 | 308 | 2022-03-24
292 | 292 | 2022-03-25
276 | 276 | 2022-03-26
260 | 260 | 2022-03-27
244 | 244 | 2022-03-28
224 | 220 | 2022-03-29
208 | 208 | 2022-03-30
208 | 208 | 2022-03-31
172 | 172 | 2022-04-01
156 | 156 | 2022-04-02
140 | 140 | 2022-04-03
128 | 128 | 2022-04-04
108 | 108 | 2022-04-05
88 | 88 | 2022-04-06
72 | 72 | 2022-04-07
56 | 56 | 2022-04-08
40 | 40 | 2022-04-09
36 | 36 | 2022-04-10
32 | 32 | 2022-04-11
16 | 16 | 2022-04-12
0 | 0 | 2022-04-13