## Estimate
SPRINT 3 PLANNING
Team Availability
| Name | Available Hours | Estimation Total
| Tien | 80 | 280 | [10 empty] | On Time
| Phuoc | 60 | [11 empty] | Lately
| Huy | 68 | [11 empty] | Early
| Dat | 72 | [11 empty] | Unfinished
Sprint | Component | Task name | Responsible Member | Total | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01
3 | Initial Sprint 3 | Sprint Planning Meeting | All member | 16 | 0
|  | Create Sprint Backlog for Sprint 3 | Tien | 4 | 4 | 0
|  | Create Test Plan document for Sprint 3 | Phuoc | 4 | 4 | 4 | 0
| Design | Design UI for Create stage and task | Dat | 2 | 2 | 0
|  | Design UI for View stage of project | Dat | 2 | 2 | 0
|  | Design UI for Report contribution | Dat | 2 | 2 | 2 | 0
|  | Design UI for Group contribution | Dat | 2 | 2 | 2 | 0
|  | Design UI for Manage Defense | Huy | 4 | 2 | 2 | 0
|  | Design Test Case | Tien | 4 | 4 | 4 | 0
| Code | [Front-end] Stage list and task [User] | Dat | 16 | 16 | 16 | 16 | 12 | 8 | 4 | 0
|  | [Front-end] View stage of project [User] | Dat | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0
|  | [Front-end] Report contribution | Dat | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0
|  | [Front-end] Create defense [Moderator] | Huy | 8 | 8 | 8 | 8 | 4 | 0
|  | [Front-end] Assign group for defense [Moderator] | Huy | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Front-end] Update defense [Moderator] | Huy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Front-end] Defense list [Moderator] | Huy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Front-end] Defense detail [Moderator] | Huy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] List stage and task [User] | Phuoc | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] View stage of project [User] | Phuoc | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] Report contribution [Student] | Phuoc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] Group contribution [Student] | Phuoc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] Create Defense [Moderator] | Tien | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] assign group for Defense [Moderator] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Update Defense [Moderator] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] List Defense [Moderator] | Tien | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] Detail Defense [Moderator] | Tien | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] Export defense list file [Moderator] | Tien | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] Delete Defense[Moderator] | Tien | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
| Testing | Test All Funtion | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Fix bug | Fix bug for Sprint 3 | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Re-testing | Re-Testing for Sprint 3 | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Close | Spring Review meeting | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
|  | Retrospective | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
|  |  |  | 280 | 262 | 254 | 240 | 224 | 208 | 192 | 176 | 160 | 144 | 128 | 112 | 96 | 80 | 64 | 48 | 32 | 16 | 0

## Actual
SPRINT 3 PLANNING
Team Availability
| Name | Available Hours | Estimation Total
| Tien | 84 | 256 | [11 empty] | On Time
| Phuoc | 80 | [12 empty] | Lately
| Huy | 64 | [12 empty] | Early
| Dat | 28 | [12 empty] | Unfinished
Sprint | Component | Task name | Responsible Member | Total | Actual | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01
3 | Initial Sprint 3 | Sprint Planning Meeting | All member | 16 | 16 | 0
|  | Create Sprint Backlog for Sprint 3 | Tien | 4 | 4 | 4 | 0
|  | Create Test Plan document for Sprint 3 | Phuoc | 4 | 4 | 4 | 4 | 0
| Design | Design UI for Create stage and task | Dat | 2 | 2 | 2 | 0
|  | Design UI for View stage of project | Dat | 2 | 2 | 2 | 0
|  | Design UI for Report contribution | Dat | 2 | 2 | 2 | 2 | 0
|  | Design UI for Group contribution | Dat | 2 | 2 | 2 | 2 | 0
|  | Design UI for Manage Defense | Huy | 4 | 4 | 2 | 2 | 0
|  | Design Test Case | Tien | 4 | 4 | 4 | 4 | 0
| Code | [Front-end] Stage list and task [User] | Dat | 16 | 0 | 16 | 16 | 16 | 12 | 8 | 4 | 0
[5 empty] | 0 |  |  |  | -4 | -4 | -4 | -4
|  | [Front-end] View stage of project [User] | Dat | 12 | -16 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0
[9 empty] | -4 | -4 | -4 | -4 | -4 | -4 | -4
|  | [Front-end] Report contribution | Dat | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0
|  | [Front-end] Create defense [Moderator] | Huy | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Front-end] Assign group for defense [Moderator] | Huy | 8 | 4 | 8 | 8 | 8 | 8 | 8 | 4 | 0
-4
|  | [Front-end] Update defense [Moderator] | Huy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Front-end] Defense list [Moderator] | Huy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Front-end] Defense detail [Moderator] | Huy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] Stage list and task [User] | Phuoc | 8 | 24 | 8 | 8 | 8 | 4 | 0
[10 empty] | 4 | 4 | 4 | 4
|  | [Back-end] View stage of project [User] | Phuoc | 8 | 12 | 8 | 8 | 8 | 8 | 8 | 4 | 0
4
|  | [Back-end] Report contribution [Student] | Phuoc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] Group contribution [Student] | Phuoc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] Create defense [Moderator] | Tien | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] Assign group for defense [Moderator] | Tien | 4 | 0 | 4 | 4 | 4 | 4 | 4 | 0
-4
|  | [Back-end] Update defense [Moderator] | Tien | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | [Back-end] Defense list [Moderator] | Tien | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] Defense detail [Moderator] | Tien | 8 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
-4
|  | [Back-end] Export defense list file [Moderator] | Tien | 8 | 20 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
[18 empty] | 4 | 4 | 4
|  | [Back-end] Delete defense[Moderator] | Tien | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
| Testing | Test All Funtion | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Fix bug | Fix bug for Sprint 3 | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Re-testing | Re-Testing for Sprint 3 | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
| Close | Spring Review meeting | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
|  | Retrospective | All member | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 0
[5 empty] | 256 | 262 | 254 | 240 | 216 | 204 | 184 | 172 | 160 | 140 | 124 | 108 | 96 | 84 | 68 | 52 | 32 | 16 | 0

## Burn Down Chart
Estimated | Actual | Date
262 | 262 | 2022-04-14
254 | 254 | 2022-04-15
240 | 240 | 2022-04-16
224 | 216 | 2022-04-17
208 | 204 | 2022-04-18
192 | 184 | 2022-04-19
176 | 172 | 2022-04-20
160 | 160 | 2022-04-21
144 | 140 | 2022-04-22
128 | 124 | 2022-04-23
112 | 108 | 2022-04-24
96 | 96 | 2022-04-25
80 | 84 | 2022-04-26
64 | 68 | 2022-04-27
48 | 52 | 2022-04-28
32 | 32 | 2022-04-29
16 | 16 | 2022-04-30
0 | 0 | 2022-05-01