## Estimate
SPRINT 4 PLANNING
Team Availability
| Name | Available Hours | Estimation Total
| Tien | 11 | 88 | [10 empty] | On Time
| Phuoc | 35 | [11 empty] | Lately
| Huy | 33 | [11 empty] | Early
| Dat | 9 | [11 empty] | Unfinished
Sprint | Component | Task name | Responsible Member | Total | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12
4 | Initial Sprint 4 | Sprint Planning Meeting | All member | 4 | 0
|  | Create Sprint Backlog for Sprint 4 | Tien | 4 | 0
|  | Create Test Plan document for Sprint 4 | Phuoc | 4 | 0
| Design | Design UI for Submit Grade of Group | Huy | 4 | 4 | 0
|  | Design Test Case | Dat | 4 | 4 | 4 | 0
|  | [Front-end] Submit Grade of Group | Huy | 16 | 16 | 16 | 16 | 12 | 8 | 4 | 0
|  | [Front-end] Report Grade of Group | Huy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] Submit Grade of Group | Phuoc | 16 | 16 | 16 | 16 | 12 | 8 | 4 | 0
|  | [Back-end] Report Grade of Group | Phuoc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 0
| Testing | Test All Funtion | All member | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Fix bug | Fix bug for Sprint 4 | All member | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Re-testing | Re-Testing for Sprint 4 | Tien, Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Close | Spring Review meeting | All member | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Retrospective | All member | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  |  | 88 | 76 | 72 | 68 | 60 | 52 | 44 | 32 | 28 | 20 | 8 | 0

## Actual
SPRINT 4 PLANNING
Team Availability
| Name | Available Hours | Estimation Total
| Tien | 11 | 88 | [11 empty] | On Time
| Phuoc | 35 | [12 empty] | Lately
| Huy | 33 | [12 empty] | Early
| Dat | 9 | [12 empty] | Unfinished
Sprint | Component | Task name | Responsible Member | Total | Actual | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12
4 | Initial Sprint 4 | Sprint Planning Meeting | All member | 4 | 4 | 0
|  | Create Sprint Backlog for Sprint 4 | Tien | 4 | 4 | 0
|  | Create Test Plan document for Sprint 4 | Phuoc | 4 | 4 | 0
| Design | Design UI for Submit Grade of Group | Huy | 4 | 4 | 4 | 0
|  | Design Test Case | Dat | 4 | 4 | 4 | 4 | 0
| Code | [Front-end] Submit Grade of Group | Huy | 16 | 16 | 16 | 16 | 16 | 12 | 8 | 4 | 0
|  | [Front-end] Report Grade of Group | Huy | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
|  | [Back-end] Submit Grade of Group | Phuoc | 16 | 16 | 16 | 16 | 16 | 12 | 8 | 4 | 0
|  | [Back-end] Report Grade of Group | Phuoc | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 4 | 0
| Testing | Test All Funtion | All member | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Fix bug | Fix bug for Sprint 4 | All member | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Re-testing | Re-Testing for Sprint 4 | Tien, Phuoc | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Close | Spring Review meeting | All member | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Retrospective | All member | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  |  |  | 88 | 88 | 76 | 72 | 68 | 60 | 52 | 44 | 32 | 28 | 20 | 8 | 0

## Burn Down Chart
Estimated | Actual | Date
76 | 76 | 2022-05-02
72 | 72 | 2022-05-03
68 | 68 | 2022-05-04
60 | 60 | 2022-05-05
52 | 52 | 2022-05-06
44 | 44 | 2022-05-07
32 | 32 | 2022-05-08
28 | 28 | 2022-05-09
20 | 20 | 2022-05-10
8 | 8 | 2022-05-11
0 | 0 | 2022-05-12